## QA-estimation for DRIVER
QA Estimation
Test Preparation | [6 empty] | Test Execution |  |  |  | Comment |  |  |  | Sub-modulewise
Screen Name | Module | Sub-Modules | Total Test Cases | Estimated time (in man days) | Requirement analysis and share understanding(in man days) | Data preparation | Total browsers | Test Cycles | Test cases | Estimated time (in man days) | [5 empty] | design & execution effort | Design & execution ratio | Review & bug fixing effort | effort
Login |  | Login | 5 | 0.15625 |  | 0.041667 | 1 | 1 | 5 | 0.083333 |  |  |  | DE effort | 7.0313 | 0.28125 | 0.04 | 0.10417 | 0.38542
Dashboard | Driver | Driver | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 |  |  |  | RB effort | 2.6042 | 0.1125 | 0.016 | 0.041667 | 0.15417
| Black Spots By Severity | Zoom in & zoom out icon | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | An icon to select STREETS & SATELLITE | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Analyze & filter | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
| Incidents: Last Two Weeks map | View all incidents | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | BJIT SQA Productivity |  |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
| Total economic loss and societal harm: Last 90 days | Loss amount | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | Task | Time(min) |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
| Number of incidents | Detail Loss amount | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | Test case preparation | 15 |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | 30 Days | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | Test execution | 8 |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | 90 Days | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | Bug report | 10 |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | 365 Days | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | Bug retest | 15 |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
| Time of Day, Day of Week: Last 90 Days | Day Name | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 |  | Review test case | 5 |  |  | 0.1125 | 0.016 | 0.041667 | 0.15417
| Saved Filters | Time | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 |  | Data Preparation | 4 |  |  | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Event count mark | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Filter Name | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Description | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | View | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
My Account | Account Information | Account Information | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
Manage Duplicate Records | Potential Duplicate Records | Potential Dublicate Records | 4 | 0.125 |  | 0.033333 | 1 | 1 | 4 | 0.066667 | [5 empty] | 0.225 | 0.032 | 0.083333 | 0.30833
Map | Filter type | Save Filters | 4 | 0.125 |  | 0.033333 | 1 | 1 | 4 | 0.066667 | [5 empty] | 0.225 | 0.032 | 0.083333 | 0.30833
|  | Clear Filters | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Add a record | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
| Control Layer Toggle | Radio | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Checkbox | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
| Zoom in & zoom out icon | Zoom in & zoom out icon | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
| Zoom to | Zoom to | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
| Draw a polygon | Draw a polygon | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
| Draw a rectangle | Draw a rectangle | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
| Layer Edit | Layer Edit | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
| Layer Delete | Layer Delete | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
| Footer | Graph | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 | [5 empty] | 0.16875 | 0.024 | 0.0625 | 0.23125
|  | Export > Custom report | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Export > Export CSV | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Traffic Enforcement Assignments | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
| Loss amount (In number) | Pop-up view | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
Record List | Filter Bar | Occured Date > From date | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Occured Date > To Date | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Weather | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | SURFACE TYPE / রাস্তার প্রকারভেদ | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | COLLISION TYPE / সংঘর্ষের ধরন আঘাত | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | ACCIDENT SEVERITY / দুর্ঘটনার মাত্রা | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | JUNCTION TYPE / সংযোগ স্থলের ধরণ | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | CONTRIBUTORY FACTOR / সহায়ক কারণ | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | DRIVER SEX / চালকের লিঙ্গ | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | PASSENGER SEX / যাত্রীর লিঙ্গ | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Saved Filters | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Clear Filters | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Add a record | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | View | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Edit | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
Add A Record | Incident Location & Time | Location field | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | Location map | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 | [5 empty] | 0.16875 | 0.024 | 0.0625 | 0.23125
|  | Latitude (Mandatory field) | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Longitude (Mandatory field) | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Occured (Mandatory field) | 3 | 0.09375 |  | 0.025 | 1 | 1 | 3 | 0.05 | [5 empty] | 0.16875 | 0.024 | 0.0625 | 0.23125
|  | Weather dropdown | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Light | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
| RCF (Road Crash Form) | RCF (Road Crash Form) | 9 | 0.28125 |  | 0.075 | 1 | 1 | 9 | 0.15 | [5 empty] | 0.50625 | 0.072 | 0.1875 | 0.69375
| ARF (Accident Report Form) | ARF (Accident Report Form) | 5 | 0.15625 |  | 0.041667 | 1 | 1 | 5 | 0.083333 | [5 empty] | 0.28125 | 0.04 | 0.10417 | 0.38542
|  | THANA / থানা | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | ARF (Accident Report Form) > VEHICLES / যানবাহনগুলি | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | VEHICLES / যানবাহনগুলি> VEHICLE / যানবাহন 1 | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | PASSENGER / যাত্রীদের বিবরণ | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | PASSENGER / যাত্রীদের বিবরণ > PASSENGER / যাত্রীর বিবরণ 1 | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | PEDESTRIAN / পথচারীদের বিবরণ | 1 | 0.03125 |  | 0.0083333 | 1 | 1 | 1 | 0.016667 | [5 empty] | 0.05625 | 0.008 | 0.020833 | 0.077083
|  | PEDESTRIAN / পথচারীদের বিবরণ > PEDESTRIAN / পথচারীর বিবরণ 1 | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | CONTRIBUTORY FACTOR / সহায়ক কারণ | 2 | 0.0625 |  | 0.016667 | 1 | 1 | 2 | 0.033333 | [5 empty] | 0.1125 | 0.016 | 0.041667 | 0.15417
|  | Total | 125 | 3.9062 | 0 | 1.0417 |  |  | 125 | 2.0833 |  |  |  |  | Ttl | 7.0312 | 1 | 2.6042 | 9.6354
| Test Management | Test Case Review | 125 | 1.3021
|  | Scrum, Meeting and Reporting | [7 empty] | 0
|  | Bug Reporting (considering 20% bug) | [6 empty] | 25 | 0.52083
|  | Bug Retesting (20% bug) | [6 empty] | 25 | 0.78125
|  | Regression Testing (considering 25% of total test cases) | [6 empty] | 0 | 0
|  | Integration Testing | [6 empty] | 0 | 0
|  | BAT | 0 | 0 |  |  |  |  | 0 | 0
|  | Basic Testing on others devices (25%) | [6 empty] | 0 | 0
|  |  | Test Preparation (Total Man Day): |  |  | 6.25 | Test Execution, Bug Reporting and Retesting Time (Total Man Day): |  |  | 3.3854
[8 empty] | Total Effort (man-day) |  | 9.6354
[8 empty] | Total Effort (man-month) |  | 0.48177
|  | SQA Velocity |  |  |  | Note:
|  | Task |  | Execution per man day |  | 1 Add notes
|  | Test case design productivity |  | 32 |  | 2
|  | Test case execution productivity |  | 60 |  | 3
|  | Test case review |  | 96 |  | 4
5